## Sheet1
Burnley NC Final Plan by CoM Priority
Design Feature/ Issue Location | What is the issue? | Why address the issue? | How to resolve the issue | Priority | What next? | Preferred product? | Why preferred? | Cost | Total costs | Monitoring?
Large gap above door between north meeting space and the passage way | Air travels freely throughout much of house making it difficult to regulate temps in much of house. Unable to effectively zone heating and cooling | Increased thermal comfort particularly in meeting rooms & kitchen; Reduced heating costs; Reduced carbon footprint | Seal the gap by extending the wall; no need to insulate as it is an interior wall | Very High | Find out if Council is going to do this | N/A |  | Covered by Council?
Large gap in wall between south meeting space & children’s room | Air travels freely between two rooms making it difficult to regulate temperature in both rooms. Unable to effectively zone heating and cooling | Increased thermal comfort particularly in meeting rooms & kitchen; Reduced heating costs; Reduced carbon footprint | 1) Install Perspex in lower half and adjustable glass louvers in upper half for air flow when needed OR 2) Cover entire gap with adjustable sash window | Very High | Find out if Council is going to do this | Perspex |  | Covered by Council?
Open "door" between kitchen and glass room and adjacent gap in wall between storage space and glass room | No door separating kitchen from glass room resulting in tremendous air leakage to and from uninsulated glass room. | Increased thermal comfort particularly in meeting rooms & kitchen; Reduced heating costs; Reduced carbon footprint | Install a door with effective draught seal; Install well sealed, adjustable glass louvers above new door for passive solar gain in winter and ventilation in summer Seal adjacent wall gap | Very High | Due to safety and access issues in this location Council will need to specify what kind of door is to code. | If code allows CoM prefers sliding door which makes best use of tight space. |  |  | 1500
External door seals in Childrens' room and South meeting space | Gaps at top and bottom of doors; Doors are poorly sealed and have single glazed glass | Increased thermal comfort; Reduced heating costs; Reduced carbon footprint | 1) Replace doors w/better insulated/sealed one – double glazed glass OR 2) Adjust doors and seal gaps with EcoMaster products | [5 empty] | 1000
Internal door seals, particularly doors within foyer and toilet doors | Gaps at bottom of doors due to uneven floors ; Doors are poorly sealed from foyer draughts | Increased thermal comfort; Reduced heating costs; Reduced carbon footprint | Adjust doors to accommodate floor and seal gaps with EcoMaster products |  |  |  | See Eco Master brochure | Approx $100 per door x four doors | 400
Insulation - Ceiling throughout the house including the kitchen and glassroom | Insulation in ceiling has some large gaps where it is either too thin or non-existent. Remaining insultation is about 6cm thick = approx R2 | A well insulated ceiling reduces winter heat loss 25 - 35% and summer heat gain 25 – 35%. Gaps in the optimal thickness of ceiling insulation can be a significant source of direct heat transfer. | Insulate with highest R value possible, smoothing out & topping up to maximize benefit. Request gone in to CoY to smooth out. | High |  | Option 1: Recommendation from Jika: GreenStuf Bulk Insulation, available from Autex Industries http://autexindustries.com/nz/insulation | Made from 100% polyester and bonded using heat instead of chemical binders. Naturally resistant to fire, moisture, vermin, insects, mould and bacteria, eliminating the need for any chemical additives. It is non-toxic, non-irritating, non-allergenic | Approximately $3,000 | 3000
Insulation - Walls | No insulation in external walls/building shell | In winter typical heat loss through uninsulated external walls is 10 – 20% In summer typical heat gain through uninsulated external walls is 15 – 25% | Insulate outer walls if possible | High | Get quotes
Glazing in Foyer, Children's room, and South meeting room - the southern wall | Top row of single glazed panes on south aspect receive no solar access & leak heat | In winter typical heat loss through windows is 11 – 20%. In summer typical heat gain through windows is 25 - 35%. The thermal performance of any solid wall is much higher than even the best windows | Remove top row of glass panes and replace with solid insulated wall | High | Get quotes |  |  | Mostly labor costs
Glazing in Children's room, and South meeting room - the southern wall | Windows on south are single glazed and have limited solar access | Double glazed windows on the south would notably enhance their thermal performance and serve as an accessible demonstration feature | Double glaze all remaining south side windows | High |  | Eco-Glaze | Eco-Glaze has many benefits - see brochure with technical information | Approximately $4234 - see quote sheet for room breakdown | 4234
Glazing in foyer | The windows are single glazed and have limited solar access; Perspects have been added as a safety features but do not function as double glaze as there are large gaps | Gaps in perspects are a safety hazard for little fingers. Double glazed windows enhance their thermal performance and serve as an accessible demonstration feature | Properly install perspects that seal well and serve as a type of cheap double glazing | High | Get quote | Perspects | No need to spend the money on Eco-Glaze as this a foyer with lots of traffic and not a room people spend time in
Windows throughout house (except toilets and storage) | Windows lack blinds and pelmets | Properly fitted and installed blinds and pelmets can enhance the thermal comfort and aesthetics as well as reduce energy costs | Install Roman blinds and pelmets with child safety features | High |  | Roman Blinds Soft Roman - back batten Cord operated Blockout lined | Due to size and location of windows as well as child safety issues Roman blinds were recommended as best choice Roman Blinds designed by LEMA Decorations in Preston; Quoted by Mychelle Potts - Watsonia GH volunteer. Pelmets designed by Allwood NH Men's Shed | costs range from $360 - $625 per room; whole house (including storage spaces) = $5,005 - see quote sheet for room breakdown; Pelmets will cost approximately $50 each | 5005
Windows in kitchen and north meeting space | Windows do not open restricting ventilation and ability to quickly cool the kitchen | Improve air quality, thermal comfort and reduce cooling costs and energy waste | Replace with double glazed sash windows that open on top and bottom; |  | Get quotes
Window in computer room | Window does not open and this room gets very warm in summer | Improve air quality, thermal comfort and reduce cooling costs and energy waste | Replace with double glazed sash sash window so it can be opened; Install a security grate on top for night purging of warm air in summer |  | Get quote
South West Toilets | Open louvered "window" in small southwest toilet | Thermal comfort of the toilet nappy changing area, south meeting space etc… is undermined by this open window | Install a sash window in the existing frame |  | Get quote
Nappy change area | Poorly ventilated area | Improve air quality, thermal comfort and reduce cooling costs and energy waste | Install wall exhaust fan in existing window space | [5 empty] | 100
Toilet in southwest block | Old full flush toilet | Wastes water | Replace with dual flush low volume toilet |  | Find specific brand |  |  |  | 500
Skylights in kitchen, north meeting space, computer room, office, office toilet | Limited natural light available in these rooms due to close proximity of adjacent building on the north side and or limitations of windows | Adequate and adjustable natural light enhances the quality and aesthetics of a space. It also reduces the need for artificial light thereby reducing energy costs and waste. | Install a well sealed, state of the art skylight/solar tube in kitchen; easy to do here with no attic |  |  | Solar tubes | See brochure for benefits | $1,185 per solar tube | 5925
Lighting in kitchen & adjacent storage space; | Fluorescent tubes extend from kitchen into storage space wasting energy by lighting up storage space which is seldom needed; Lighting in most rooms could be improved | Unnecessary and inefficient lighting affects visual quality, wastes energy and money | Reduce the number of fluorescent lights in the kitchen to what is appropriate for the space. Install a separate, single Led light in the storage room. Also, if needed, other lights throughout house should be replaced with appropriate, energy efficient bulbs |  | Get quote from electrician
External Shading for office, computer room, glassroom | Uncomfortably warm on hot days due room size, # of users, # of computers and glare from windows; | Currently split system A/C is used to cool down these rooms with limited effectiveness. Reduce glare, energy costs and emissions. | Install awnings that can be adjusted based on season |  |  | See quote sheets for product information |  | Quotes range from $2,480 - $4,648 | 4648
Passive heating system located in attic | Use of mechanical heating and cooling is expensive, wasteful and increases carbon footprint | Lots of attic space which collects and stores heat in cooler weather | Install a passive heat capture system to take advantage of heat and circulate it throughout the house to reduce need for mechanical heating |  |  | Smart Breeze system | See brochure for benefits |  | 4600
Heating and Cooling system | Current patchwork system is inefficient, wasteful and performs poorly in retaining thermal comfort | Comfort, cost and conservation | Research options |  |  | Hydronic heating option too expensive at $15,000
Water capture & storage | Water from roof is not currently used to it’s potential | Save water, money & energy and demonstrate benefits | Install water tanks and plumbing; See Helen’s plan |  |  | Quote from Solar flow for 10,000 litres for all water requirements | Tankworks steel slimline tank. 1150mm wide x 3.3mtr long x 2mtr tall. Gal, delivered. 7090ltrs; 1200mm wide x 3mtrs tall. In Gal, delivered. 3400ltrs each. | $18233 for top of the line system, | 18233
Renewable Energy | House is well oriented with plenty of unshaded roof space for PV panels | Possible to provide much of BNC energy and encourage sustainability; great demonstration feature | Install PV panels | Mid | Virginia Researched and got quotes |  |  | Option 1A: $14,318 or $8,990 after credits & discount Option 1B: $19,021 or $12,990 after credits & discount Option 2A: $9,301 or $3,474 after credits & discount Option 2B: $11,463 or $5,174 after credits & discount | 11463
Total | [8 empty] | 60608
Glass Room
Envelope of room | Rounded shape and poor design of this very popular room undermines ability to effectively retrofit this space | Heating and cooling this room is very costly in terms of money and the environment; Consistent thermal comfort is very difficult to achieve in this room in the warmer and colder months | Rebuild the room with higher standards that proactively address passive solar design | High but cost may be prohibitive
Shading | Uncomfortably warm on hot days. Currently split system A/C is used to cool down room with limited effectiveness. | The energy cost of operating split system air conditioner(A/C) is very high and wasteful. Reduce glare, energy costs and emissions. | Install removable/adjustable shade sail above glass room to screen south and west exposures. Remove in winter | High
Insulation | No insulation in ceiling of glass room | In winter typical heat loss through an uninsulated ceiling is 25 – 35% | Install insulation between the ceiling beams; Check with asbestos issue | High
In summer typical heat gain through an uninsulated ceiling is 25 – 35%
Thermal Mass | Currently the thermal mass potential of the concrete floor is being squandered as a result of the lack of insulation, single glazed glass and existing gaps to external and internal walls. | Thermal mass can help regulate the temperature within this room so there is less need for mechanical heating and cooling | See sections on passive solar heating, insulation and glazing | High
Windows | Windows lack insulating curtains and pelmets to contain warm and cool air | Properly fitted and installed curtains and pelmets can significantly enhance the thermal comfort and aesthetics as well as reduce energy costs and waste | Install full length curtains and pelmets with child safety features – though may be difficult with rounded walls | High
Glazing | Windows on south aspect are single glazed and have limited solar access | Double glazed windows on the south would notably enhance their thermal performance and serve as an accessible demonstration feature | Double glaze all remaining south side windows | Mid